|  |  |  |
| --- | --- | --- |
| number | Name of research activity | Number of days or duration |
| 1 | Review literature review on information security and systems | 5 days |
| 2 | Design questionnaire and interview guide | 6 days |
| 3 | Visit schools and work places for interviews | 1 week |
| 4 | Review notes from interviews and process data from questionnaires | 2 weeks |
| 5 | Define functional and non-functional requirements of the expert information security system | 1 week |
| 6 | Design data flow for expert information security system | 5 days |
| 7 | Implement expert information security system | 2 weeks |
| 8 | Test and validate expert information security system | 1 week |
| 9 | Write and submit report | 2 weeks |

RESEARCH PLAN